## Start Here
The One-Person AI Department Toolkit
Step | What to do | Use this sheet
1 | Audit recurring work for AI fit. | AI Opportunity Audit
2 | Define the few AI roles you actually need. | Role Roster
3 | Turn repeated work into documented workflows. | Workflow Builder
4 | Increase automation only after reliability is proven. | Automation Canvas
5 | Measure time saved, quality, errors and owner involvement. | Weekly Scorecard
6 | Use the roadmap to mature the department over 90 days. | 90-Day Roadmap

## AI Opportunity Audit
AI Opportunity Audit
Activity | Business Function | Trigger | Frequency | Minutes Each Time | Repeatability (1–5) | Business Value (1–5) | Judgment Required (1–5) | Risk (1–5) | AI Fit (1–5) | Recommended Bucket | Priority Score

## Role Roster
AI Department Role Roster
Role | Mission | Responsibilities | Inputs | Resources / Context | Outputs | Quality Standard | Authority | Restrictions | Escalation Rules
AI Chief of Staff
AI Research Analyst
AI Marketing Specialist
AI Sales Assistant
AI Operations Coordinator
AI Customer Support Specialist

## Workflow Builder
Universal AI Workflow Builder
Workflow | Business Outcome | Trigger | Required Inputs | AI Instructions | Processing Steps | Quality Check | Human Review | Output | Destination | Exception / Escalation

## 25 Workflow Library
25 Starter AI Workflows
# | Workflow | Best used for | Suggested human checkpoint
1 | Morning CEO briefing | Recurring one-person business workflow | Review before external action or commitment
2 | Weekly business review | Recurring one-person business workflow | Review before external action or commitment
3 | Competitor intelligence report | Recurring one-person business workflow | Review before external action or commitment
4 | Customer interview analysis | Recurring one-person business workflow | Review before external action or commitment
5 | Meeting preparation | Recurring one-person business workflow | Review before external action or commitment
6 | Meeting-to-action workflow | Recurring one-person business workflow | Review before external action or commitment
7 | Market research | Recurring one-person business workflow | Review before external action or commitment
8 | Content research | Recurring one-person business workflow | Review before external action or commitment
9 | Content repurposing | Recurring one-person business workflow | Review before external action or commitment
10 | Campaign development | Recurring one-person business workflow | Review before external action or commitment
11 | Prospect research | Recurring one-person business workflow | Review before external action or commitment
12 | Sales-call preparation | Recurring one-person business workflow | Review before external action or commitment
13 | Proposal creation | Recurring one-person business workflow | Review before external action or commitment
14 | Sales follow-up | Recurring one-person business workflow | Review before external action or commitment
15 | Customer onboarding | Recurring one-person business workflow | Review before external action or commitment
16 | Customer support response | Recurring one-person business workflow | Review before external action or commitment
17 | Voice-of-customer analysis | Recurring one-person business workflow | Review before external action or commitment
18 | Project status reporting | Recurring one-person business workflow | Review before external action or commitment
19 | SOP creation | Recurring one-person business workflow | Review before external action or commitment
20 | Document summarization | Recurring one-person business workflow | Review before external action or commitment
21 | Contract obligation extraction | Recurring one-person business workflow | Review before external action or commitment
22 | Expense-analysis preparation | Recurring one-person business workflow | Review before external action or commitment
23 | Monthly management reporting | Recurring one-person business workflow | Review before external action or commitment
24 | Vendor comparison | Recurring one-person business workflow | Review before external action or commitment
25 | Quarterly strategic review | Recurring one-person business workflow | Review before external action or commitment

## Automation Canvas
AI Automation Canvas
Workflow | Trigger | Systems / Tools | AI Decision | Autonomy Level (0–4) | Human Approval Point | Risk | Exception Rule | Logging / Audit Trail | Kill Switch

## Quality Checklist
AI Quality-Control Checklist
Check | Required? | Completed? | Notes
Facts verified | Yes
Numbers recalculated | Yes
Sources/date checked | Yes
Names/titles correct | Yes
Tone matches business | Yes
No unsupported claims | Yes
Privacy reviewed | Yes
Customer data protected | Yes
Output meets format | Yes
Human approval completed where required | Yes

## Weekly Scorecard
Weekly AI Department Scorecard
Week | Workflow / Role | Runs | Minutes Saved per Run | Total Hours Saved | Quality (1–5) | Errors | Owner Minutes | Revenue Supported / Cost Avoided | What to Improve

## 30-Day Plan
30-Day AI Department Implementation Plan
Week | Focus | Action | Owner | Status | Evidence / Result
Week 1 | Audit | Inventory recurring work and select five AI candidates.
Week 2 | Build | Define roles, tools, Company Brain and core context.
Week 3 | Systematize | Build executive, research and revenue/customer workflows.
Week 4 | Measure | Add safe automation, quality checks and scorecard.

## 90-Day Roadmap
90-Day AI Department Maturity Roadmap
Phase | Days | Objective | Build / Improve | Measure | Decision Gate
Foundation | 1–30 | Build context and first reliable workflows | Company Brain, roles, first 3 workflows | Time saved, quality, intervention | Do the workflows earn trust?
Integration | 31–60 | Connect workflows and reduce handwork | Handoffs, automation, monitoring | Cycle time, errors, owner minutes | Which steps can gain autonomy?
Optimization | 61–90 | Scale what works and retire what does not | Role refinement, dashboards, more workflows | ROI, quality trend, cost avoided | What becomes standard operating capability?

## Prompt Patterns
15 Practical Prompt Patterns
# | Pattern | How to use it
1 | Give the role and objective first | Adapt this pattern to the role, workflow and business context in front of you.
2 | Provide business context | Adapt this pattern to the role, workflow and business context in front of you.
3 | Define the audience | Adapt this pattern to the role, workflow and business context in front of you.
4 | Supply source material | Adapt this pattern to the role, workflow and business context in front of you.
5 | Specify the decision to support | Adapt this pattern to the role, workflow and business context in front of you.
6 | Request a structured output | Adapt this pattern to the role, workflow and business context in front of you.
7 | Ask for assumptions to be stated | Adapt this pattern to the role, workflow and business context in front of you.
8 | Require source/date verification | Adapt this pattern to the role, workflow and business context in front of you.
9 | Ask for alternatives before recommendation | Adapt this pattern to the role, workflow and business context in front of you.
10 | Separate facts from interpretation | Adapt this pattern to the role, workflow and business context in front of you.
11 | Set a quality standard | Adapt this pattern to the role, workflow and business context in front of you.
12 | Define what not to do | Adapt this pattern to the role, workflow and business context in front of you.
13 | Provide a strong example | Adapt this pattern to the role, workflow and business context in front of you.
14 | Ask for a self-check | Adapt this pattern to the role, workflow and business context in front of you.
15 | Specify escalation when uncertain | Adapt this pattern to the role, workflow and business context in front of you.